## Project Name
Big Data Bootcamp Project - Group 3
Go Live: Feb 9
Deliverable: final project
Past Due | 2022-01-10 |  |  |  |  | Team Update
Due soon | 2022-01-15 |  |  |  |  | Program Manager Update
Action Item | Due Date | Status | Module | Assigned To | Support | Comments
Deliverable 1
Decide on Project Topic | 2022-01-09 |  | Project Manager
Prep project management docs: WBS,Team Charter, Gantt | 2022-01-04 | In progress | Project Manager |  |  | 01/04 DS- Danielle to prepare initial documentation; tbd team member to vet requirements/dependencies
Schedule and hold Kickoff meeting with team | 2022-01-04 | complete | Project Manager
Align on Team Charter and Responsibility Matrix | 2022-01-05 | In progress | Project Manager | Team |  | 01/08 DS - Team charter and communication protocols have alignment. Need to determine role assignment.
Research project topics/potential datasets | 2022-01-05 | complete | Team | Team
Schedule & hold Project Topic Meeting | 2022-01-06 | complete | Project Manager |  |  | 01/06 DS - Meeting scheduled for 01/06 9pm; all team members to do research and pitch 1-2 projects for consideration.
Obtain concensus on project topic | 2022-01-06 | complete | Project Manager |  |  | 01/07 DS - Aligned on proposing Sunshine list; back up single-family home rentals
Create List of questions to be answered/ problem to be solved/ answer why topic | 2022-01-06 | In progress | Project Manager |  |  | 01/08 DS - preliminary list of questions identified
Presentation | 2022-01-09
Draft ReadMe file for project topic proposal | 2022-01-07 | In progress | X Role | Danielle
Communication Protocols (Team Charter) | 2022-01-07 | complete | Project Manager |  |  | 01/06 DS - Final draft Team Charter updated and posted to team slack channel.
Obtain approval for Project Proposal | 2022-01-10 |  | Team
Present project proposal to Sal/TA's | 2022-01-10 |  | Team
GitHub | 2022-01-09
Create ReadMe.md | 2022-01-07 |  | Square Role
The descriptions and explanations required in all other project deliverables | 2022-01-09 |  | Square Role
Description of the communication protocols | 2022-01-07 | In progress | Square Role
Create Github repo | 2022-01-07 |  | Square Role | Shaza
Create main branch | 2022-01-07 |  | Square Role | Shaza
Create individual branches (1 per team member) | 2022-01-07 |  | Square Role | Shaza
GitHub Commits (4 commits per team member) | 2022-01-08 |  | Team
4 commits/PR | 2022-01-08 |  | Square Role
4 commits/PR | 2022-01-08 |  | Triangle Role
4 commits/PR | 2022-01-08 |  | Circle Role
4 commits/PR | 2022-01-08 |  | X Role | Danielle
Machine Learning Model | 2022-01-09
Build mock up of machine learning model (takes in data/outputs labels for input data) | 2022-01-08 |  | Triangle Role
Develop a diagram that explains how it will work concurrently with the rest of the project steps | 2022-01-08 |  | Triangle Role
Database Integration | 2022-01-09
Source dataset | 2022-01-07 |  | Circle Role
for mock up - use kaggle csv
Clean dataset and organize dataset - document process | 2022-01-07 |  | Circle Role
Create an ERD | 2022-01-09 |  | Circle Role
Exploritory Analysis | 2022-01-07 |  | Circle Role
Creat a sample DataBase; providing sampe data that minics final db structure | 2022-01-07 |  | Circle Role
Connection between db and machine learning module | 2022-01-08 |  | Circle Role
Dashboard |  | NA
Determine technologies to be used for pipeline | 2022-01-09 |  | X Role
Create Project Proposal for instructor approval | 2022-01-09 |  | X Role
Deliverable 2
Presentation
Draft google slide presentation to include: ✓ Selected topic ✓ Reason why they selected their topic ✓ Description of their source of data ✓ Questions they hope to answer with the data ✓ Description of the data exploration phase of the project ✓ Description of the analysis phase of the project | 2022-02-07 |  | X Role
Create a storyboard |  |  | X Role
GitHub
Main Branch - code is production ready and includes: ✓ All code necessary to perform exploratory analysis ✓ Some code necessary to complete the machine learning portion of the project |  |  | X Role
Individual Branches ✓ At least one branch for each team member ✓ Each team member has at least four commits for the duration of the second segment (eight total commits per person) |  |  | X Role
4 commits/PR |  |  | Square Role
4 commits/PR |  |  | Triangle Role
4 commits/PR |  |  | Circle Role
4 commits/PR |  |  | X Role
README.md must include: ✓ Description of the communication protocols ✓ The descriptions and explanations required in all other project deliverables ✓ Outline of the project (this may include images, but should be easy to follow and digest) |  |  | Square Role
Machine Learning Model
Team members submit the code for their machine learning model, as well as the following: ✓takes in data/outputs labels for input data ✓ Description of preliminary data preprocessing ✓ Description of preliminary feature engineering and preliminary feature selection, including their decision-making process ✓ Description of how data was split into training and testing sets ✓ Explanation of model choice, including limitations and benefits |  |  | Triangle Role
Jupyter Notebook/python code |  |  | Triangle Role
Process Documentation |  |  | Triangle Role
Reports and/or image captures |  |  | Triangle Role
Database Integration
Database stores static data for use during the project |  |  | Circle Role
Database interfaces with the project in some format (e.g., scraping updates the database, or database connects to the model) |  |  | Circle Role
webscrape https://www.ontario.ca/page/public-sector-salary-disclosure and create 1996 to 2020 data |  |  | Circle Role
Min 2 tables using database or collections for Mongo |  |  | Circle Role
Includes at least one join using the database language (not including any joins in Pandas) |  |  | Circle Role
Sample Data that mimics database structure |  |  | Circle Role
Includes at least one connection string (using SQLAlchemy or PyMongo) to draft Machine Learning Model |  |  | Circle Role
ERD with relationships (SQL) |  |  | Circle Role
Dashboard
A blueprint for the dashboard is created and includes all of the following: ✓ Storyboard on Google Slide(s) ✓ Description of the tool(s) that will be used to create final dashboard ✓ Description of interactive element(s) |  |  | X Role
Deliverable 3
Presentation
Preliminary Google Slides Presentation (refining the draft into a final version). To include: P Selected topic ✓ Reason why they selected their topic ✓ Description of their source of data ✓ Questions they hope to answer with the data ✓ Description of the data exploration phase of the project ✓ Description of the analysis phase of the project ✓ Technologies, languages, tools, and algorithms used throughout the project
GitHub
Main Branch - code is production ready and includes: ✓ All code necessary to perform exploratory analysis ✓ MOST code necessary to complete the machine learning portion of the project
Individual Branches ✓ At least one branch for each team member ✓ Each team member has at least four commits for the duration of the third segment (twelve total commits per person)
4 commits/PR |  |  | Square Role
4 commits/PR |  |  | Triangle Role
4 commits/PR |  |  | Circle Role
4 commits/PR |  |  | X Role
README.md must include: ✓ The descriptions and explanations required in all other project deliverables ✓ Outline is now cohesive and structured (may include images) ✓ Link to Google Slides draft presentation
Description of communication protocols in README are removed
Machine Learning Model
Team members submit the code for their machine learning model, as well as the following: ✓ Description of data preprocessing ✓ Description of feature engineering and preliminary feature selection, including their decision-making process ✓ Description of how data was split into training and testing sets ✓ Explanation of model choice, including limitations and benefits ✓ Explanation of changes in model choice (if changes occurred between the Segment 2 and Segment 3 deliverables) ✓ Description of how they have trained the model thus far, and any additional training that will take place ✓ Description of current accuracy score
Jupyter Notebook/python code
Process Documentation
Reports and/or image captures
Database Integration |  | NA |  |  |  | deliverables completed in segment 2
Database stores static data for use during the project
Database interfaces with the project in some format (e.g., scraping updates the database, or database connects to the model)
Min 2 tables using database or collections for Mongo
Includes at least one join using the database language (not including any joins in Pandas)
Includes at least one connection string (using SQLAlchemy or PyMongo)
ERD with relationships (SQL)
Dashboard
Dashboard is created and includes all of the following: ✓Images from the initial analysis ✓Data (images or report) from the machine learning task ✓ At least one interactive element
Deliverable 4
Presentation
Preliminary Google Slides Presentation (refining the draft into a final version). To include: P Selected topic ✓ Reason why they selected their topic ✓ Description of their source of data ✓ Questions they hope to answer with the data ✓ Description of the data exploration phase of the project ✓ Description of the analysis phase of the project ✓ Technologies, languages, tools, and algorithms used throughout the project ✓ Result of analysis ✓ Recommendation for future analysis ✓ Anything the team would have done differently
Google Slides Presentations are finalized in Google Slides. ✓ Slides are primarily images or graphics (rather than primarily text) ✓ Images are clear, in high-definition, and directly illustrative of subject matter
Live Presentation ✓ All team members present in equal proportions ✓ The team demonstrates interactivity of dashboard in real time ✓ The presentation falls within any time limits provided by instructor ✓ Submission includes speaker notes, flashcards, or a video of the presentation rehearsal
Demo Video
GitHub
Main Branch - code is production ready and includes: ✓All code necessary to perform exploratory analysis ✓ All code necessary to complete machine learning portion of project ✓ All code is clean, commented, easy to read, and adheres to a coding standard (e.g., PEP8)
Any images that have been created (at least three)
Create Requirements.txt file
Individual Branches ✓ At least one branch for each team member ✓ Each team member has at least four commits for the duration of the third segment (sixteen total commits per person)
4 commits/PR |  |  | Square Role
4 commits/PR |  |  | Triangle Role
4 commits/PR |  |  | Circle Role
4 commits/PR |  |  | X Role
README.md must include: ✓ The descriptions and explanations required in all other project deliverables ✓ Any images that have been created (at least three) ✓ Outline is now cohesive and structured (may include images) ✓ Link to dashboard (or link to video of dashboard demo) ✓ Link to Google Slides FINAL presentation
Machine Learning Model
Team members submit the code for their machine learning model, as well as the following: ✓ Description of data preprocessing ✓ Description of feature engineering and preliminary feature selection, including their decision-making process ✓ Description of how data was split into training and testing sets ✓ Explanation of model choice, including limitations and benefits ✓ Explanation of changes in model choice (if changes occurred between the Segment 2 and Segment 3 deliverables) ✓ Description of how model was trained (or retrained, if they are using an existing model) ✓ Description and explanation of model’s confusion matrix, including final accuracy score
Jupyter Notebook/python code
Process Documentation
Reports and/or image captures
If statistical analysis is not included as part of the current analysis, include a description of how it would be included in the next phases of the project.
Database Integration |  | NA |  |  |  | deliverables completed in segment 2
Database stores static data for use during the project
Database interfaces with the project in some format (e.g., scraping updates the database, or database connects to the model)
Min 2 tables using database or collections for Mongo
Includes at least one join using the database language (not including any joins in Pandas)
Includes at least one connection string (using SQLAlchemy or PyMongo)
ERD with relationships (SQL)
Dashboard
Dashboard is created and includes all of the following: ✓Images from the initial analysis ✓Data (images or report) from the machine learning task ✓ At least one interactive element
Dashboard is published or the submission includes a screen capture video of it in action

## Instruction on Template use
Action Category and sub-cateogry bands must be format painted into the appropriate section •this will ensure the conditional formating on due date and status functions for task lines
To Be Assigned
Project Manager
Team
Square Role
Triangle Role
Circle Role
X Role
Ben
Danielle
Justin
Shaza
Team